ACTION LOG: SUMMARY OF ACTIONS FROM BOARD MEETING(S)

UPDATED: 19.05.26

| MEETING | SUBJECT | ACTION SUMMARY | WHO | DATE BY | UPDATE / OUTCOME | STATUS: |
| --- | --- | --- | --- | --- | --- | --- |
| 7/06/2023 and ongoing | Dundee Heritage Walks | Existing leaflets to be reprinted and new leaflets to be designed. | AF/AMS | 31.03.26 | New leaflets printed. Electronic versions still to be updated. Amanda liaising with Altar staff. MixMap have said they will add our walks to the city trails section of their Dundee tourist guide. | Ongoing |
| 6/09/2023 4/12/2024 And ongoing | Bell Street plaque | Investigate installing a plaque to Bell Street disaster | GM/AMS/MH |  | Anita Bell: The Music Hall Society have funded a blue plaque and this is ready and waiting for the appropriate event/date to install (in association with Dr Billy Rough); it is hoped that this will be during the exhibition at the McManus. | Ongoing |
| 03/12/25 | Employee Handbook | Drafts for discussion / agreement | AF/VK | January 2026 | Following feedback from SCVO, Amanda has completed the handbook and the final version is now available in the portal. | Complete |
| 4/09/2024 4/12/2024 5/03/25 | Looking Up Schools Project | Doug progressing ideas from his paper on a possible schools project. | DB/JG/MH |  | Looking at possible changes. Update: MH taking this forward with DB and schools. | On hold due to other commitments. |
| 21/10/25 | HES Funding Application | Following the request and approval for a six month extension period, the new final submission will be for 31.03.26 | MH/AF/SC/AMS | 31/03/26 | The application was submitted and we await feedback from HES. | Complete |
| 03.12.25 | Bank account access | Vanessa, Mylene and Amanda to have direct access to the bank account | AMS/VK/AF | January 2026 | Bank mandate was rejected due to confusion over who is a current signatory. | Ongoing |
| 03.12.25 | Meeting and reports structure | The reports for each meeting are not necessarily in the most helpful place. | AF/MH/BI | June 2026 | The grants report has been refined and will be trialled at the June meeting. | Ongoing |