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ACTION LOG: SUMMARY OF ACTIONS FROM BOARD MEETING(S)
UPDATED: 19.05.26
	MEETING
	SUBJECT
	ACTION SUMMARY
	WHO
	DATE BY
	UPDATE / OUTCOME
	STATUS:

	
	
	
	
	
	
	

	7/06/2023
and ongoing
	Dundee Heritage Walks
	Existing leaflets to be reprinted and new leaflets to be designed.
	AF/AMS
	31.03.26
	New leaflets printed. Electronic versions still to be updated. Amanda liaising with Altar staff. MixMap have said they will add our walks to the city trails section of their Dundee tourist guide.  
	Ongoing

	6/09/2023
4/12/2024
And ongoing
	Bell Street plaque
	Investigate installing a plaque to Bell Street disaster
	GM/AMS/MH
	
	Anita Bell: The Music Hall Society have funded a blue plaque and this is ready and waiting for the appropriate event/date to install (in association with Dr Billy Rough); it is hoped that this will be during the exhibition at the McManus.  
	Ongoing

	03/12/25
	Employee Handbook
	Drafts for discussion / agreement 
	AF/VK
	January 2026
	Following feedback from SCVO, Amanda has completed the handbook and the final version is now available in the portal.
	Complete

	4/09/2024
4/12/2024
5/03/25
	Looking Up Schools Project
	Doug progressing ideas from his paper on a possible schools project.
	DB/JG/MH
	
	Looking at possible changes.
Update: MH taking this forward with DB and schools. 

	On hold due to other commitments.

	21/10/25
	HES Funding Application
	Following the request and approval for a six month extension period, the new final submission will be for 31.03.26
	MH/AF/SC/AMS
	
31/03/26
	The application was submitted and we await feedback from HES. 
	Complete

	03.12.25
	Bank account access
	Vanessa, Mylene and Amanda to have direct access to the bank account 
	AMS/VK/AF
	January 2026
	Bank mandate was rejected due to confusion over who is a current signatory. 
	Ongoing

	03.12.25
	Meeting and reports structure
	The reports for each meeting are not necessarily in the most helpful place.
	AF/MH/BI
	June 2026
	The grants report has been refined and will be trialled at the June meeting.
	Ongoing
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